Guy’s & St Thomas’ NHS Foundation Trust

Sign up to Safety

Safety Improvement Plan

Contents

- Background to the Trust

- Quality and Safety at GSTT

- Our safety pledges

- Safety Improvement Projects

- Appendices:

- Appendix 1: NHSLA bid – Maternity Workstream

- Appendix 2: NHSLA bid – Children’s Workstream

- Appendix 3: NHSLA bid – Discharge Workstream

- Appendix 4: GSTT Quality Priorities 2014/15

- Sign up to Safety Team:

- Executive Sponsor:

- Ron Kerr, Chief Executive

Sign up to Safety Lead:

- Dr Adrian Hopper, Deputy Medical Director: Quality Improvement & Patient Safety

Campaign Ambassadors:

- Patricia Snell, Deputy Director Quality Improvement & Patient Safety

- Katrina Cooney, Deputy Chief Nurse

- Julie Frolich, Consultant Midwife

- Kaye Wilson, Clinical Governance Lead for Women's Services

- Sara Hanna, Evelina London Children’s Hospital Medical Director

- Claire Lemer, Consultant in General Paediatrics & Service Transformation

- Alice Oborne, Consultant Pharmacist for Safe Medication Practice

- Scott Pendleton, Head of Service for Nutrition & Dietetics

QIPS support:

- Linnie Pontin, Senior QIPS Manager

- Hannah Wierzbicki, QIPS Projects Co-ordinator.

1.0 Background to the Trust

Guy’s and St Thomas’ NHS Foundation Trust is one of the largest acute trusts in the country, and includes St Thomas’ Hospital, Guy’s Hospital, Evelina London Children’s Hospital and community services in Lambeth and Southwark.

The Trust provides a full range of hospital services for local communities in Lambeth, Southwark and Lewisham, as well as specialist services for patients from further afield, including cancer, cardiothoracic, women’s and children’s services, kidney care and orthopaedics. We have one of the largest critical care units in the UK and one of the busiest A&E departments in London.

We have more than 2 million patient contacts a year, including 866,000 in community services, 82,500 daycases, 83,000 inpatients and 1.03 million outpatients. 184,000 patients use our emergency services each year and we deliver more than 6,800 babies. We have more than 1,100 beds.

GSTT has one of the lowest mortality rates in the NHS in England, including out-of-hours and at weekends. In 2013 the Dr Foster Hospital Guide awarded us Trust of the Year for safe care.

2.0 Quality and Safety at GSTT

Guy’s and St Thomas’ works tirelessly to ensure that the care provided to patients is safe, effective and high quality. Our approach and commitment is set out in the annual Quality Priorities (appendix 2 attached). Within this, there are 14 priorities related to patient safety, which include e-noting, handover, pressure ulcers, infection control, Never Events, WHO surgical safety checklist, falls and catheter associated urinary tract infections. These are closely monitored by the board and the results published annually.

Underpinning these priorities is a comprehensive programme of quality improvement and patient safety. The Trust has made significant progress in reducing avoidable harm across a range of safety critical areas, including falls, VTE, acutely ill patients, handover, implementation of the WHO surgical safety checklist, catheter associated urinary tract infections, medicines safety and improvements to the discharge process. These projects are coordinated and monitored via the Patient Safety Improvement Forum, which is chaired by the Deputy Medical Director for Patient Safety and Quality Improvement and reports to the Trust Risk and Quality Committee.

In November 2010 the Trust held the first Safety Connections conference as part of a week long series of quality and safety events, this has now grown in to a yearly event that is held for staff and students across King’s Health Partners (KHP, which includes Guy’s & St Thomas’, King’s College Hospital, South London & Maudsley and King’s College London) we have also developed the Safety Connections Network which connects staff and students across KHP via E-mail’s, newsletters and quarterly evening events where there are opportunities to hear speakers, network and share learning. The network has also developed multi-disciplinary working groups of staff across KHP looking at areas of improvement. Safety topics covered at our network events have included Duty of Candour, WHO Surgical Safety Checklist, local innovation, organisational resilience and the Health Care Improvement Networks Patient Safety Collaborative.

The Trust publishes key information on quality on its external website, under ‘Our Quality Story’ (http://www.guysandstthomas.nhs.uk/about-us/quality-story/our-quality-story.aspx). The aim is that patients, families and healthcare professionals have access to information on how the Trust is performing. This information includes data on infection control, waiting times, and incidents and Never Events. This demonstrates the Trust’s commitment to openness and honesty in relation to quality and safety.

3.0 Our safety pledges

The Trust is proud to have joined Sign up to Safety, and to have made a public commitment to reduce avoidable harm at GSTT by 50%. We are embedding the 5 pledges listed below across the organisation, and we will be focussing on four main areas, which are set out in more detail in the safety improvement plans below.

Our safety pledges are as follows:

1. Put Safety First. Commit to reduce avoidable harm in the NHS by half and make public our goals and plans developed locally.

We will make sure our staff have the right skills, information and support to put patient safety first by:

- Developing a comprehensive register of harms that occur in our healthcare settings, including patients in the community or during handover of care to the community.

- Ensuring we have easily available and clear information for our staff and patients on known risks and what help is available to reduce incidence.

- Ensuring that training and staff development responds to regular analyses of what is reported improving the recognition and reporting of harms relating to medicines management and discharge from hospital.

- Developing robust targets to underpin our efforts to reduce the highest risk harms reported.

2. Continually learn. Make our organisation more resilient to risks, by acting on the feedback from patients and by constantly measuring and monitoring how safe our services are.

We will improve our reporting of risks and clinical incidents and make sure that actions and learning from these incidents are acted upon, by:

- Making sure that staff involved in incidents receive support.

- Ensuring high quality feedback on the actions taken in response to incidents.

- Inviting patients to sit as members of all our safety committees and ensuring that they have sufficient support and mentoring so that the patient voice is heard.

- Extending our reported outcome measures so that they include shared measures that are co-produced with our patients.

3. Honesty. Be transparent with people about our progress to tackle patient safety issues and support staff to be candid with patients and their families if something goes wrong.

We will embed an understanding of Duty of Candour in a way that it becomes part of everybody’s daily activities, by.

- Clear support including mentoring for our staff that have to deal with incidents in particular serious incidents.

- We will develop a culture in which staff never hesitate to raise a concern if they feel safety is compromised.

4. Collaborate. Take a leading role in supporting local collaborative learning, so that improvements are made across all of the local services that patients use.

We will ensure multidisciplinary approaches to safety issues and work with patients and carers to agree our priorities

We will take a leading role in the work of the collaborative patient safety networks (Health Innovation Network (South London), CLARC - South London Research Network, King’s Improvement Science, King’s Health Partners Safety Connections, GSTT Resilience Research Group) by:

- Active participation.

- Supporting staff and students who want to join collaborative learning, evaluation or research programmes linked to these.

5. Support. Help people understand why things go wrong and how to put them right. Give staff the time and support to improve and celebrate the progress.

We will listen to our staff, our patients and their carers.

We will celebrate those staff that make significant contributions towards improved patient safety, particularly in the areas that are high priority.

We will improve our support for staff in developing their knowledge and leadership skills relating to harm reduction and quality improvement.

We will establish Schwartz Rounds to provide a forum for staff to discuss difficult and emotional issues that arise when caring for patients.

4.0 Safety improvement projects

Guy’s and St Thomas’ has chosen to focus on four areas for improvement as part of the Sign up for Safety Project. These topics were chosen in consultation with senior staff across the organisation, and were chosen on the basis that they have real potential for improvement. It is anticipated that these will be built into our Quality Priorities for 2015/16.

The following topics have been selected for inclusion in our safety improvement plan:

- Maternity services: Obstetric Anal Sphincter Injuries (OASI)

- Children’s services: the deteriorating child.

- Medicine management at discharge and shortly after discharge

- Improving recognition and treatment of malnutrition

4.1 Maternity services: Obstetric Anal Sphincter Injuries (OASI)

There has been a three-fold rise in OASIs (commonly known as 3rd and 4th degree tears) in the past ten years which cannot be explained by increased risk factors. There is an element of better detection but this cannot explain it in full. The GSTT audit data is consistent with national findings. There has been a change of practice concurrent with the rise, including midwives moving away from ‘hands on’ to ‘hands poised/off’, obstetricians moving away from routine episiotomy at instrumental delivery and a poorer understanding of the physiology and mechanism of birth. There is a 5.9% incidence of OASIS which equals 48,000 new cases (Patterns of Maternity Care in English NHS Hospitals 2012. RCOG press).

At Guy’s and St Thomas’ there has been a total of 147 Obstetric Anal Sphincter Injuries reported (April 2009-January 2015). Reporting of these types of injuries has increased over the last five years which is indicative of a good patient safety reporting culture. Last year (13/14) 49 incidents were reported. These incidents are reported due to the harm caused to the patient, not due to the fact the tear was preventable or attributable to the care GSTT provided.  Themes include increased risk of 3rd and 4th degree tears when labour proceeds rapidly.

The financial and litigation costs for OASIs is estimated £48 million per annum (DoH). Costs include surgical repair in theatre and consumables used during follow-up e.g. endo-anal ultrasound, manometry, and the potential cost of a caesarian section next time. The NHSLA report 441 claims litigation claims related to OASI (fourth highest number of claims in obstetrics) (2000-2010). The total value of those claims is estimated to be £31.2million.

Recent evidence suggests that OASIs may be preventable. In Norway, following re-introduction of ‘hands-on’ and episiotomy training in a cohort of 40,000 women OASIS decreased from 4.16-5.25% before the intervention to 1.73% during the last year (p<0.001) (Hals et al). At the Mayday Hospital and in Plymouth they have had similar reductions in OASIS following training and introduction of the Norway techniques.

What is PEACHES?

P = Position

E = Extra midwife (present at birth)

A = Assess the perineum (throughout)

C = Communication

H = Hands-on technique

E = Episiotomy if required

S = S-L-O-W-L-Y

Rationale for PEACHES?

- OASI is preventable harm

- There has been a move away from an almost exclusively ‘hands-on’ technique in the mid 20th Century to 50/50 ‘hands-on’ or ‘hands-poised/off’ in recent years corresponding with the rise in OASIS – UK and other countries

- There is a great deal of confusion amongst midwives and student midwives and junior doctors regarding perineal management at birth

- NO woman wants an OASI

- We are involved in the RCOG/RCM joint initiative to reduce OASIS and improve outcomes for women

| What does success look like? What is your goal statement? | All clinical staff to be aware of PEACHES and to undertake the training. A 50% reduction in the rate of OASI at midwife-led births and a 25% reduction of OASI at obstetric-led births by the end of 2015. The elimination of 3rd and 4th degree tears. |
| --- | --- |
| Measures | OASIs will be monitored on an ongoing basis and progress reported every month at the Women’s Services Clinical Governance Group meeting. OASI is included in the Trust’s maternity incident trigger list and reported on Datix. Each OASI will be reviewed by the Maternity Risk Management Team. Number of staff trained in PEACHES will be monitored and reported on a monthly basis. The incidence of OASI will be re-audited after a full year of PEACHES. |
| What do we need to do for that success to be realised? | All clinicians attending births at GSTT to adopt PEACHES. Support will be provided by the Practice Development Midwives, senior midwives and senior obstetricians. PEACHES training will be included at all new staff induction and at mandatory training. Monthly feedback of data to clinicians. Case discussion with individual clinicians |
| What resources do we need? | I.T support in the provision of data. Mandatory training. |
| Actions | Monitor and report the rate of OASI on a monthly basis. Monitor and report the number of staff trained in PEACHES on a monthly basis. |

Leads: Julie Frolich, Consultant Midwife; Kaye Wilson, Clinical Governance Lead: Women’s Services; and the Practice Development Midwives team.

4.2 Children’s services: the deteriorating child

In focusing on this topic, we would like to see a children’s hospital in which children who deteriorate, or have the potential to deteriorate, are proactively managed throughout their inpatient stay, with all relevant members of the care team aware of any potential for deterioration. In the last five years there have been a total of 160 incidents concerning a delay or failure to monitor a child or baby. Reporting has increased over the years but last year saw a 42% decrease in incidents of this type with 37 reported in 2012/2013 and 26 in 2013/2014. The most common incident theme with a total of 36 incidents reported was due to a device failure, the majority of these concerning glucose meters. This would result in a delay in monitoring glucose levels which in turn could cause harm to a sick patient, these types of incidents are bought to the attention of the medical devices team.

| What does success look like? What is your goal statement? | Appropriate recognition and management of a deteriorating child would rely on precise and timely handovers, and accurate documentation. Success would include early recognition of the deteriorating child, appropriate escalation, and timely and effective mitigation of clinical safety risks. Appropriate escalation would rely on a culture in which staff always feel able to raise their concerns, and to have these listened to and acted upon. Effective mitigation would be underpinned by high-quality paediatric acute illness training for all paediatric staff, and evidence-based guidelines. Improving communication is a key pillar of the program: communication between team members, between different teams, and with patients and families. (Supported by high-quality, easy to understand, written patient information). There is also a role for primary prevention of deterioration, by avoiding hospital-acquired infections, and safe medicines management. There are occasional deteriorations which are unavoidable in spite of these measures. These would be subject to careful review, to identify potentials for improvements in safety practice. |
| --- | --- |
| Measures | We will measure a range of different process and outcome measures. The most important are related to measures or harm, or potential harm, due to failure to recognise, escalate or mitigate risk in a deteriorating child. Specific indicators which will be measured every 90 days include: - Respiratory and cardiac arrests - Unplanned transfers to PICU, particularly unstable transfers to PICU e.g. intubation on the ward - Unplanned transfers to higher levels of care - Length of stay in PICU - Hospital acquired infections - Serious incidents - Medicines safety incidents - Safety huddles – reliability of these - Use of SBAR - Outcomes of PICU unplanned admission case reviews - Qualitative data on safety culture (how confident staff feel to manage a deteriorating child and to raise concerns) |
| What do we need to do for that success to be realised? | - Documentation: e-noting, and/or easy availability of all required notes. - Handover: timely, with all appropriate people, succinct, using SBAR. - Recognition: easy-to-use and easy-to-interpret observation charts. - Escalation: clear escalation pathway. Regular safety huddles, which happen reliably and with all appropriate team members. - PICU outreach. - Mitigation: PAIM course for all staff. Clinical simulation. - Guidelines which are easy to find as soon as they are needed, and are simple to interpret follow. - Communication: patient information leaflets for common conditions. Safety huddles also help improve communication. - Prevention: good infection control Antibiotic stewardship. Safe medicines management, which could be considerably improved by using e-prescribing. Review: regular review meetings of unplanned admissions to PICU |
| What resources do we need? | - E-noting system, including electronic patient lists to replace Word documents, updated with information from PIMS. - Improved observation charts. - Training: including use of observation charts, safety huddles conduct. - Increased availability of PAIM (Paediatric Acute Illness Management) course. - Simulation training: staff costs and equipment maintenance. - Guidelines production and access. - New patient information leaflets. - Infection control support - E-prescribing. Culture shift to focus on prevention |
| Actions | The following measures will be monitored every 90 days: - Respiratory and cardiac arrests - Unplanned transfers to PICU, particularly unstable transfers to PICU e.g. intubation on the ward - Unplanned transfers to higher levels of care - Length of stay in PICU - Hospital acquired infections - Serious incidents - Medicines safety incidents - Safety huddles – reliability of these - Use of SBAR Outcomes of PICU unplanned admission case reviews. |

Leads: Ronny Cheung, Consultant: General Paediatrics; Claire Lemer, Consultant in General Paediatrics & Service Transformation; Isabel Stanley, Clinical Governance Facilitator: Evelina London and Rosanna Bevan, Quality Improvement Fellow at Evelina London.

4.3 Medicine management at discharge and shortly after discharge

At Guy’s and St Thomas’, 875 incidents have been reported in the last five years relating to medication errors at discharge or shortly after. There has been a 65% increase in reporting of these incidents since 2010. The most common theme is omitted medicine when TTOs are provided or the wrong medicine being provided at discharge. After discharge, dose or strength being wrong or unclear was a common reported theme with 59 being reported in total. There has been an increase, year on year on these types of incidents reported. To date 187 incidents have been reported this current financial year which is already more than the 184 reported last year (2013/2014). This area is also a concern for patients, GPs and commissioners. We have received several quality alerts from GPs and commissioners highlighting communication issues and errors around medications on discharge. There have also been incidents highlighting problems with GPs and patients acting on information about medicines on discharge information. Patient surveys have shown we could improve the information we provide for patients on medication at discharge to enable them to better understand and manage their medication.

We would like to see a reduction in medication-related problems immediately after discharge. This includes verbal and written communication at discharge with patients, carers and community health professionals. The goal is to reduce the harm associated with use of medicines at discharge and assess the baseline extent of harm from pain, readmissions and communication failure. We also plan to engage the relevant stakeholders in IT, hospital and community.

| What does success look like? What is your goal statement? | The goal is to reduce the harm associated with use of medicines at discharge by half. The proposed areas are: - Improving pain symptoms for patients discharged on new analgesics for example post-operatively - Improve the written communication at discharge (in line with NHSE/MHRA alert 2014 communication at discharge). - Reduce medication-related readmissions to the older persons unit |
| --- | --- |
| Measures | 1. Pain scale scores for patients discharged on opioid analgesics after elective orthopaedic surgery 2. Patients who report they have received information dose adjustment (titration down) of opioid analgesics post-operatively 3. Proportion of patients who report they have received information on changed to their medication regimen at discharge 4. Proportion of inpatient discharge letter that state the reasons why drug that have been stopped, started or doses changes. 5. Medicines monitoring advice and action to be taken, in the discharge letter 6. Number of readmissions to the Older Persons Unit which have medication as a contributing factor 7. Time taken to send a discharge communication to community pharmacists and other community-based providers. |
| What do we need to do for that success to be realised? | 1. We need patients to be able to better manage their analgesics at home, for better pain control. E.g. patient knowledge of the new medicines and what to do if problems or pain. Multidisciplinary staff will improve communication including written communication with patients and carers before discharge 2. Written discharge communication needs changes, e.g. improve documentation of reasons for stopping, starting or change doses of medications. 2b.In addition, communication of medication monitoring or actions by the community health professionals e.g. GPs. 3. Robust systems for secure electronic communication of discharge letter with community pharmacists (after patient has consented). 4. Robust and quick processes for patients at medication risk to be referred to community-based health professionals e.g. pharmacists after discharge. |
| What resources do we need? | 1. We need resources to design build and test a resilient process for patient/carer medicines information before discharge, including time to conduct assessments such as patient surveys 2. Communications. We need resources to develop systems to enhance communication about medicines changes 3. electronic systems We need systems to communicate easily with patients’ named community-based carers including pharmacists for specific patients 4. Review the ways of working of community-based medicines experts. |
| Actions | 1. Build the multidisciplinary, cross-sector team of people to improve medication errors and reduce harm, after discharge 2. Meeting with stakeholders including IT to outline the extent and type of harm from discharge letter failings 3. Meeting with stakeholders in the community to understand how they believe communication at discharge can be improved 4. Table paper at Trust MSF and at EDL group. |

Leads: Alice Oborne, Consultant Pharmacist: Safe Medication Practice.

4.4 Improving recognition and treatment of malnutrition

To improve the recognition of malnutrition, the treatment of those recognised as at risk and to improve the care planning and continuity of care for those patients on discharge from hospital.

| What does success look like? What is your goal statement? | The goal is to maintain and improve the nutritional status of every patient admitted to the trust and communicate the patients’ needs appropriately on discharge. - Every patient will be weighed and under go nutritional screening on admission and weekly thereafter during their admission. - Drug charts will contain current and accurate weights for patients to enable safe and effective treatment - Every admitted patient will have a Nutrition care plan that is updated on a regular basis - Referrals relating to nutrition made in a timely fashion - Information relating to the nutrition of the patient will be added to all discharge documentation. |
| --- | --- |
| Measures | - Number of patients with a fully completed Nutrition Screening tool on admission - Number of patients with a fully completed up to date screening tool during their admission. - Weight change during admission - Number of patients with a Nutrition care plan that is relevant and up to date. - Percentage of patients identified as at risk who are Referred to Dietetics % of Electronic Discharge Letters (EDL) containing nutrition related communication. |
| What do we need to do for that success to be realised? | - Ward teams need to understand the importance of weighing patients and of nutrition screening - A programme of training and communication needs to be put in place - Review current Nutrition care planning processes and documentation Review and improve the systems for communication and referral internally and onward (this includes a review and the EDL). |
| What resources do we need? | - Every ward must have appropriate equipment for weighing, heighting and supporting patients’ nutrition. - Need opportunity to review and change the EDL - Supportive documentation must be reviewed and improved and made easily and accessible for staff. - Need opportunity to review and change the systems for communication with external agencies involved in the support of patients nutrition on discharge Availability and appropriateness of food, snacks and nutritional feed products will be reviewed and changed if appropriate. |
| Actions | 1. Establish a multidisciplinary working group. 2. Design Audit Tool to establish baseline data. 3. Complete audit for nutrition screening tool and care planning. 4. Design a training plan with respect to nutrition. 5. Agree a plan for roll out of training plan. 6. Review documentation relating to Nutrition. 7. Review system for onward referral into the community. - Agree plan for audit cycle regarding nutrition. |

Leads: Scott Pendleton, Head of Service for Nutrition & Dietetics and Julie Murray, Senior Nurse: Chief Nurse’s Office.